S 12-D2 Telework implementation methodology

Obsah

# 1. 	Telework

Telework main features							1

2. 	Preparation of telework implementation				2

2.1 	Setting the targets and performance indicators			2

2.2	The extent of telework							2

2.3	Getting support for a telework program				2

2.4	Program coordinator 							2

2.5	Methodology for evaluation of the program				2

2.6	The program budget							3

2.7	Setting the selection criteria						3

2.8	Compilation of the necessary documentation			4

3	Realisation of telework in the workplace 				5

4	Monitoring and evaluation						5

4.1	Evaluation of results and reports					6

# 1. Telework

Telework main features:

- Use of information and telecommunication technologies

- Significant work is carried out outside the permanent employer site

- Flexibility – time, place and system of work is the subject of mutual agreement between the employer and employee

- Voluntariness – work in the form of teleworking can be arranged only on the basis between the employer and employee

- Egality – working conditions of teleworkers are the same as employees working in the employer site

- Stability – a job is defined in an employment contract

- Regularity – regular nature of the work in agreed terms and intervals

2.  Preparation of telework implementation

Successful implementation of telework at the workplace is subjected by agreement and support from the side of management. If there are some uncertainties concerning the meaning of the telework introduction, its actual implementation will be very difficult.

2.1.

Setting the targets and performance indicators

Before the implementation of telework in the practice of the organization is essential to set up the goals that should be reached through telework realization. Equally important is to establish performance indicators to measure the results achieved against the set goals.

2.2.

The extent of telework

Recommended procedure: 
• Submit the draft of telework program to the management and to get feedback from him

• Assess what support that can be expected from the management side
• Compare the feasibility of a the pilot program and the complete program in terms of the organization size, allocated budget and the number of participants 
• Decide whether a pilot program shall be launched or not 
• Determine the extend of the program 
• Work out the documents which will define telework in the workplace, set up the goals and tasks of program

2.3.

Getting support for a telework program

At a time when the launch of the program (the implementation of telework) is thought about is important to suppose that not everyone heard about it and will encouraged it. In this case it is appropriate to promote the presentation of this program and its promotion, the best way is to start from the senior management of the organization.

2.4.

Program Coordinator

The program coordinator plays decisive role in the introduction of telework in the organization. In order to carry out effectively his activities it is needed for program coordinator to have guaranteed immediate access to management and continuous support throughout the process of the program implementation. His advantage is if he is experienced in introducing of new programs, respectively in preparation of new corporate policies. An important prerequisite for the success of his work is to be employed full-time job mainly in the initial stage of a telework implementation. 
2.5.

Methodology for evaluation of the program

The measurement of the telework successfullness is an important prerequisite for its enforcement particularly in relation to the management.

The evaluation should consist of this following elements:

- determine the extend of the evaluation

- choice of assessment tools

- reporting of program activities

- obtaining the information

- analysis of the obtained information

- treatment of evaluation reports and found results presentation

2.6.

The program budget

The correct setting of the budget is the determining factor for the success of its implementation. The budget should consider the items relative to workers, administrative costs, office equipment and technology, setting up working areas to perform the telework program and to evaluate it.

- cost of staff (both internal and external)

- administrative costs

- cost of equipment and purchase of communication devices

- cost of setting up office/workplace

- cost of the evaluation of the program

2.7.

Setting the selection criteria

The main feature of Teleworking is voluntariness. 
The employer and employee assume that work in the form of telework is beneficial for both parties. However, it is important to remember that not every employee may be suitable as teleworkers. It is necessary to choose the proper selection criteria to ensure that program participants are suitable for telework as well as the nature of work enables its performance by telework system. Similarly, the managerial procedures of supervisors must meet the work conditions in form of teleworking.

Basic characteristics of the work of appropriate for telework: 
- The minimum level of personal communication (face to face) 
- Adjustable course of the work 
- Autonomy 
- Access to resources 
- Access to sensitive information 
- Simple use of technology 
Basic characteristics of the worker suitable for telework: 
- Willingness to work in form of teleworking 
- Very good knowledge of its work 
- Ability to plan and organize its work 
- Minimum need for supervision (control) 
- Ability to work independently 
- Very good communication skills 
Basic features of telework supervisor: 
- Positive attitude to telework 
- Management through achieved results 
- Flexibility 
- Excellent communication skills 
- Ability to plan and organize work 
- Trust - reliance on subordinated teleworkers

2.8.

Compilation of the necessary documentation

Well-prepared documentation will help the implementation of telework, participants selection, their training and monitoring the achieved results. The extent of documentation will depend on the workers number included in the plan, set goals and tasks and on the scope of plan – if it is a pilot program or not. Documentation may not be completely in advance before starting the program. It can be compiled step by step according to what the program will require.

Selection questionnaires

Questionnaire for the control group:

Training documentation

Evaluation documentation

Individual surveys

Work reports 
Time Recorder 
Checklist of health and safety at the teleworker workplace

Checklists are used to eliminate any shortages in the teleworker workplace before the start of program. They should be specifically tailored to the work conditions at teleworker home and cover all aspects - lighting, heat, noise, safety of electrical wiring and connection of devices, etc..

  - Rules to work in form of Telework (Telework Policy)

  - It is possible to include form of Telework to the working procedures worked-out by the Department of Human Resources of Organization.

  - The document should include this points: 
- Employment conditions
- Extent of working time 
- Method for the absence reporting
- Daily working program 
- Health and safety at work of employees 
- Provision of furniture, hardware and services
- Safety 
- Costs, expenses 
- Access to the data of employer

Telework agreement

Telework agreement is a formal document that describes the contractual requirements and conditions to conduct the work in the form of telework, responsibilities and obligations of teleworker and organization. Its purpose is to provide teleworker and his employer a clear terms of work performance within the telework program and expected results.

The conclusion of such agreement (contract) should be formal and voluntary act and expects the signature by both parties before the beginning of telework so that it is clear that both parties read it and understood its contents.

3.

Realisation of telework in the workplace

Immediately after suitable work activities were identified that can be performed by telework, it is possible to select suitable employees.

Selection can be provided formally through formal questionnaires completed by eligible employees or informal way through discussions with them to find their interest in telework.

Formal way is better when considering a larger number of workers who have the interest to engage the agenda or in the case the pilot program starts. This will allow better evaluation of the effectiveness of the selection process.

6 steps to select suitable teleworkers: 
1st 	Support the program 
2nd 	Telework presentation 
3rd 	Teleworkers selection
4th 	Supervisors selection
5th 	Selection of the control group members
6th 	Participation of household members

4.

Monitoring and evaluation

After the successful launch of the program it is important to get information about its smooth application and in the case of found problems these can be immediately solved. It is necessary to make sure that the program evaluation plan is functional and that on its basis is possible to prepare a analysis and report of gathered data.

Permanent support of the program include:

- Support from the program coordinator side

- Support from the management and supervisor side

- Mutual support of teleworkers themselves

- Support from colleagues side

The best way to manage teleworkers is to manage them depending on the final results. Supervisor and teleworkers work together to achieve real results and they monitor the achievement of these results by:

- clearly defined performance targets as supervisor, as well as teleworkers are jointly agree on the specific results to be achieved

- precise planning of the work as a supervisor and teleworkers can accurately suggest the timing and resource requirements

- structure of continuous problem solution, because the supervisor has a good overview of the first-hand communication problems occured and can assist in solving them.

Clear definition of teleworkers goals should reflect:

- What is to be done

- How it should be achieved

- Who is responsible for the particular work

- When the work should be completed

- What procedure should be chosen

- Why the work should be performed

- What are the necessary resources

- Who is responsible for coordinating the various component of work

- Criteria for measuring outcomes

Teleworkers work appreciation 
Teleworkers can be exposed to the fear of being less visible, they themselves as well as the results of their work. In order to counteract these fears the supervisors can apply the following steps:

- Appreciate the exceptional (superior) work performance

- encourage teleworkers to achieve better results

- to inform top management about the quality of the work results of teleworkers

- to make sure the teleworkers that they have the opportunity to participate in the new tasks of the organization

Problems related to the work of teleworkers may result from:

- delay in identifying the necessary resources

- communication difficulties

- lack of cooperation with colleagues

- lack of necessary equipment

- negligence of raised requirements

4.1.

Evaluation of results and reports

The success of the program generally depends on a formal evaluation of its course. The evaluation should include all participants.

Suitable strategies to obtain the greatest number of evaluation materials:

- sending the personal letters to all program participants and ask them for submission of evaluation materials in time; at the same time it is need to ensure them that all their completed evaluation materials will be treated with discretion and will only be used for the program purpose;

- distribution and collection of questionnaires in the course of program activities such as training program of participants or target groups meetings

- personal address those who have not submitted completed evaluation materials in a time and provide them sheets to fill again.

Analysis of gained results

The method of analysis, survey and conclusions draft depends on whether there are or not necessary skills and resources to do the analysis and compare the answers against to the questions.

Quality communication is the most effective way to maintain interest and viability of the program. Positive, constructive communication is essential between top management and senior management, between the senior and middle management, between the middle management between teleworkers and between teleworkers and between teleworkers and supervisors and colleagues.